## Ticket_Management
Total Tickets | 105
Overdue Tickets | 58
Completed Tickets | 27
High Priority Tickets | 33
Tickets With Comments | 1
Ticket ID | Request Type | Priority | Status | Assigned To | SLA (hrs) | Created Date | SLA Due Date | Date Resolved | Overdue? | Comments
TCK-007 | Profile Update | High | Completed | Sneha | 48 | 2025-11-15 20:00 | 2025-11-17 20:00 | 2025-11-16 01:00 | On-Time
TCK-008 | Email Notification Issue | High | Closed | Lokesh | 12 | 2025-11-17 12:00 | 2025-11-18 | 2025-11-18 05:00 | On-Time
TCK-010 | Course Mapping | High | Closed | Arjun | 12 | 2025-11-15 23:00 | 2025-11-16 11:00 | 2025-11-16 09:00 | On-Time
TCK-013 | Course Access Issue | High | Closed | Sneha | 36 | 2025-11-13 22:00 | 2025-11-15 10:00 | 2025-11-14 14:00 | On-Time
TCK-023 | Password Reset | High | Completed | Lokesh | 12 | 2025-11-17 21:00 | 2025-11-18 09:00 | 2025-11-18 04:00 | On-Time
TCK-024 | Password Reset | High | Closed | Sneha | 48 | 2025-11-12 01:00 | 2025-11-14 01:00 | 2025-11-13 12:00 | On-Time
TCK-036 | LMS Registration | High | Completed | Lokesh | 12 | 2025-11-12 15:00 | 2025-11-13 03:00 | 2025-11-12 20:00 | On-Time
TCK-042 | Course Access Issue | High | Completed | Rahul | 12 | 2025-11-13 12:00 | 2025-11-14 | 2025-11-14 01:00 | On-Time
TCK-044 | LMS Registration | High | Completed | Arjun | 12 | 2025-11-16 18:00 | 2025-11-17 06:00 | 2025-11-17 05:00 | On-Time
TCK-048 | Profile Update | High | Completed | Sneha | 12 | 2025-11-12 05:00 | 2025-11-12 17:00 | 2025-11-13 01:00 | On-Time
TCK-061 | LMS Registration | High | Completed | Rahul | 12 | 2025-11-16 12:00 | 2025-11-17 | 2025-11-16 18:00 | On-Time
TCK-070 | Certificate Download | High | Closed | Lokesh | 24 | 2025-11-17 04:00 | 2025-11-18 04:00 | 2025-11-17 05:00 | On-Time
TCK-076 | Email Notification Issue | High | Completed | Sneha | 12 | 2025-11-17 14:00 | 2025-11-18 02:00 | 2025-11-17 16:00 | On-Time
TCK-085 | Password Reset | High | Completed | Arjun | 24 | 2025-11-13 14:00 | 2025-11-14 14:00 | 2025-11-14 01:00 | On-Time
TCK-087 | Course Enrollment | High | Completed | Arjun | 36 | 2025-11-10 19:00 | 2025-11-12 07:00 | 2025-11-11 23:00 | On-Time
TCK-089 | Course Access Issue | High | Closed | Nisha | 24 | 2025-11-11 11:00 | 2025-11-12 11:00 | 2025-11-12 17:00 | On-Time
TCK-001 | Password Reset | Low | Closed | Sneha | 12 | 2025-11-17 20:00 | 2025-11-18 08:00 | 2025-11-18 08:00 | On-Time
TCK-016 | Password Reset | Low | Completed | Arjun | 12 | 2025-11-12 05:00 | 2025-11-12 17:00 | 2025-11-12 16:00 | On-Time
TCK-019 | Course Mapping | Low | Closed | Rahul | 48 | 2025-11-16 09:00 | 2025-11-18 09:00 | 2025-11-16 22:00 | On-Time
TCK-033 | Learning Path Issue | Low | Completed | Lokesh | 24 | 2025-11-14 02:00 | 2025-11-15 02:00 | 2025-11-15 02:00 | On-Time
TCK-034 | Course Mapping | Low | Completed | Lokesh | 36 | 2025-11-16 04:00 | 2025-11-17 16:00 | 2025-11-16 20:00 | On-Time
TCK-037 | Password Reset | Low | Completed | Lokesh | 48 | 2025-11-17 22:00 | 2025-11-19 22:00 | 2025-11-18 18:00 | On-Time
TCK-043 | Email Notification Issue | Low | Completed | Sneha | 12 | 2025-11-13 03:00 | 2025-11-13 15:00 | 2025-11-13 05:00 | On-Time
TCK-050 | Email Notification Issue | Low | Completed | Sneha | 12 | 2025-11-17 04:00 | 2025-11-17 16:00 | 2025-11-17 15:00 | On-Time
TCK-060 | LMS Registration | Low | Completed | Sneha | 36 | 2025-11-17 17:00 | 2025-11-19 05:00 | 2025-11-18 22:00 | On-Time
TCK-064 | Certificate Download | Low | Completed | Sneha | 12 | 2025-11-17 12:00 | 2025-11-18 | 2025-11-17 19:00 | On-Time
TCK-067 | Certificate Download | Low | Completed | Lokesh | 24 | 2025-11-11 16:00 | 2025-11-12 16:00 | 2025-11-12 13:00 | On-Time
TCK-073 | LMS Registration | Low | Closed | Lokesh | 36 | 2025-11-16 15:00 | 2025-11-18 03:00 | 2025-11-18 13:00 | On-Time
TCK-097 | Password Reset | Low | Closed | Nisha | 48 | 2025-11-14 02:00 | 2025-11-16 02:00 | 2025-11-14 14:00 | On-Time
TCK-002 | Course Access Issue | Medium | Closed | Arjun | 48 | 2025-11-12 05:00 | 2025-11-14 05:00 | 2025-11-13 03:00 | On-Time
TCK-006 | Profile Update | Medium | Closed | Rahul | 36 | 2025-11-13 21:00 | 2025-11-15 09:00 | 2025-11-15 16:00 | On-Time
TCK-015 | Course Access Issue | Medium | Completed | Rahul | 24 | 2025-11-12 08:00 | 2025-11-13 08:00 | 2025-11-12 23:00 | On-Time
TCK-018 | Password Reset | Medium | Completed | Sneha | 12 | 2025-11-15 13:00 | 2025-11-16 01:00 | 2025-11-16 03:00 | On-Time
TCK-020 | Course Access Issue | Medium | Closed | Nisha | 12 | 2025-11-15 15:00 | 2025-11-16 03:00 | 2025-11-16 06:00 | On-Time
TCK-021 | Course Enrollment | Medium | Completed | Sneha | 24 | 2025-11-12 12:00 | 2025-11-13 12:00 | 2025-11-12 17:00 | On-Time
TCK-025 | Profile Update | Medium | Completed | Nisha | 48 | 2025-11-13 04:00 | 2025-11-15 04:00 | 2025-11-14 18:00 | On-Time
TCK-030 | Profile Update | Medium | Closed | Sneha | 24 | 2025-11-14 05:00 | 2025-11-15 05:00 | 2025-11-15 14:00 | On-Time
TCK-045 | Access Issue | Medium | Completed | Rahul | 24 | 2025-11-13 09:00 | 2025-11-14 09:00 | 2025-11-13 17:00 | On-Time
TCK-057 | Access Issue | Medium | Completed | Lokesh | 48 | 2025-11-17 12:00 | 2025-11-19 12:00 | 2025-11-18 07:00 | On-Time
TCK-062 | Email Notification Issue | Medium | Closed | Nisha | 24 | 2025-11-12 01:00 | 2025-11-13 01:00 | 2025-11-13 08:00 | On-Time
TCK-077 | LMS Registration | Medium | Completed | Lokesh | 36 | 2025-11-13 02:00 | 2025-11-14 14:00 | 2025-11-13 22:00 | On-Time
TCK-093 | Course Access Issue | Medium | Completed | Arjun | 36 | 2025-11-11 23:00 | 2025-11-13 11:00 | 2025-11-13 09:00 | On-Time
TCK-009 | Password Reset | High | In Progress | Nisha | 36 | 2025-11-15 07:00 | 2025-11-16 19:00 |  | Overdue
TCK-014 | Password Reset | High | In Progress | Lokesh | 36 | 2025-11-13 19:00 | 2025-11-15 07:00 |  | Overdue
TCK-022 | Profile Update | High | In Progress | Arjun | 24 | 2025-11-18 07:00 | 2025-11-19 07:00 |  | Overdue
TCK-027 | Profile Update | High | New | Nisha | 24 | 2025-11-13 17:00 | 2025-11-14 17:00 |  | Overdue
TCK-035 | Profile Update | High | New | Nisha | 48 | 2025-11-18 12:00 | 2025-11-20 12:00 |  | Overdue
TCK-046 | Password Reset | High | Assigned | Lokesh | 36 | 2025-11-12 18:00 | 2025-11-14 06:00 |  | Overdue
TCK-047 | Certificate Download | High | Assigned | Arjun | 36 | 2025-11-15 12:00 | 2025-11-17 |  | Overdue
TCK-052 | Email Notification Issue | High | In Progress | Nisha | 12 | 2025-11-17 18:00 | 2025-11-18 06:00 |  | Overdue
TCK-053 | Certificate Download | High | New | Rahul | 36 | 2025-11-15 08:00 | 2025-11-16 20:00 |  | Overdue
TCK-055 | LMS Registration | High | In Progress | Rahul | 24 | 2025-11-13 07:00 | 2025-11-14 07:00 |  | Overdue
TCK-058 | Course Access Issue | High | New | Arjun | 36 | 2025-11-12 05:00 | 2025-11-13 17:00 |  | Overdue
TCK-071 | Course Access Issue | High | New | Sneha | 12 | 2025-11-12 05:00 | 2025-11-12 17:00 |  | Overdue
TCK-075 | Access Issue | High | Assigned | Nisha | 24 | 2025-11-14 02:00 | 2025-11-15 02:00 |  | Overdue
TCK-084 | Access Issue | High | New | Arjun | 12 | 2025-11-10 13:00 | 2025-11-11 01:00 |  | Overdue
TCK-088 | Profile Update | High | New | Rahul | 24 | 2025-11-10 13:00 | 2025-11-11 13:00 |  | Overdue
TCK-095 | LMS Registration | High | Assigned | Arjun | 12 | 2025-11-13 23:00 | 2025-11-14 11:00 |  | Overdue
TCK-098 | Learning Path Issue | High | In Progress | Arjun | 12 | 2025-11-15 04:00 | 2025-11-15 16:00 |  | Overdue
TCK-005 | Certificate Download | Low | New | Rahul | 24 | 2025-11-13 16:00 | 2025-11-14 16:00 |  | Overdue
TCK-026 | Profile Update | Low | Assigned | Sneha | 48 | 2025-11-10 12:00 | 2025-11-12 12:00 |  | Overdue
TCK-028 | Course Access Issue | Low | Assigned | Sneha | 24 | 2025-11-14 00:00 | 2025-11-15 |  | Overdue
TCK-029 | LMS Registration | Low | New | Rahul | 12 | 2025-11-14 10:00 | 2025-11-14 22:00 |  | Overdue
TCK-031 | Profile Update | Low | In Progress | Arjun | 36 | 2025-11-15 05:00 | 2025-11-16 17:00 |  | Overdue
TCK-038 | Access Issue | Low | Assigned | Lokesh | 36 | 2025-11-18 09:00 | 2025-11-19 21:00 |  | Overdue
TCK-039 | Password Reset | Low | Assigned | Lokesh | 48 | 2025-11-15 14:00 | 2025-11-17 14:00 |  | Overdue
TCK-040 | Access Issue | Low | New | Arjun | 24 | 2025-11-17 15:00 | 2025-11-18 15:00 |  | Overdue
TCK-041 | LMS Registration | Low | New | Lokesh | 24 | 2025-11-18 10:00 | 2025-11-19 10:00 |  | Overdue
TCK-049 | Course Enrollment | Low | New | Nisha | 36 | 2025-11-15 16:00 | 2025-11-17 04:00 |  | Overdue
TCK-051 | Certificate Download | Low | New | Nisha | 24 | 2025-11-14 06:00 | 2025-11-15 06:00 |  | Overdue
TCK-054 | Access Issue | Low | New | Arjun | 48 | 2025-11-15 08:00 | 2025-11-17 08:00 |  | Overdue
TCK-059 | Password Reset | Low | Assigned | Rahul | 12 | 2025-11-11 12:00 | 2025-11-12 |  | Overdue
TCK-063 | Password Reset | Low | Assigned | Sneha | 36 | 2025-11-10 10:00 | 2025-11-11 22:00 |  | Overdue
TCK-065 | Password Reset | Low | In Progress | Rahul | 12 | 2025-11-10 19:00 | 2025-11-11 07:00 |  | Overdue
TCK-068 | Course Mapping | Low | New | Nisha | 48 | 2025-11-11 04:00 | 2025-11-13 04:00 |  | Overdue
TCK-074 | Learning Path Issue | Low | Assigned | Rahul | 36 | 2025-11-10 16:00 | 2025-11-12 04:00 |  | Overdue
TCK-081 | LMS Registration | Low | New | Sneha | 48 | 2025-11-14 07:00 | 2025-11-16 07:00 |  | Overdue
TCK-082 | Access Issue | Low | Assigned | Arjun | 48 | 2025-11-12 22:00 | 2025-11-14 22:00 |  | Overdue
TCK-083 | Course Access Issue | Low | In Progress | Lokesh | 36 | 2025-11-18 17:00 | 2025-11-20 05:00 |  | Overdue
TCK-090 | Profile Update | Low | New | Nisha | 36 | 2025-11-14 02:00 | 2025-11-15 14:00 |  | Overdue
TCK-091 | Course Mapping | Low | New | Nisha | 12 | 2025-11-14 23:00 | 2025-11-15 11:00 |  | Overdue
TCK-092 | Learning Path Issue | Low | In Progress | Arjun | 48 | 2025-11-14 19:00 | 2025-11-16 19:00 |  | Overdue
TCK-094 | Course Access Issue | Low | In Progress | Rahul | 36 | 2025-11-12 02:00 | 2025-11-13 14:00 |  | Overdue
TCK-096 | Certificate Download | Low | New | Arjun | 48 | 2025-11-15 21:00 | 2025-11-17 21:00 |  | Overdue
TCK-099 | Access Issue | Low | In Progress | Lokesh | 36 | 2025-11-17 09:00 | 2025-11-18 21:00 |  | Overdue
TCK-100 | Course Mapping | Low | New | Nisha | 12 | 2025-11-12 03:00 | 2025-11-12 15:00 |  | Overdue
TCK-003 | Course Enrollment | Medium | In Progress | Sneha | 48 | 2025-11-17 07:00 | 2025-11-19 07:00 |  | Overdue
TCK-004 | Certificate Download | Medium | Assigned | Arjun | 48 | 2025-11-18 08:00 | 2025-11-20 08:00 |  | Overdue
TCK-011 | Course Enrollment | Medium | New | Nisha | 48 | 2025-11-17 01:00 | 2025-11-19 01:00 |  | Overdue
TCK-012 | Profile Update | Medium | Assigned | Lokesh | 12 | 2025-11-14 18:00 | 2025-11-15 06:00 |  | Overdue
TCK-017 | Profile Update | Medium | In Progress | Lokesh | 48 | 2025-11-16 00:00 | 2025-11-18 |  | Overdue
TCK-032 | Course Mapping | Medium | Assigned | Nisha | 24 | 2025-11-12 12:00 | 2025-11-13 12:00 |  | Overdue
TCK-056 | Course Access Issue | Medium | New | Lokesh | 24 | 2025-11-14 03:00 | 2025-11-15 03:00 |  | Overdue
TCK-066 | Learning Path Issue | Medium | Assigned | Lokesh | 36 | 2025-11-11 03:00 | 2025-11-12 15:00 |  | Overdue
TCK-069 | Profile Update | Medium | New | Sneha | 12 | 2025-11-13 15:00 | 2025-11-14 03:00 |  | Overdue
TCK-072 | Profile Update | Medium | Assigned | Rahul | 36 | 2025-11-18 04:00 | 2025-11-19 16:00 |  | Overdue
TCK-078 | Course Mapping | Medium | In Progress | Rahul | 24 | 2025-11-18 00:00 | 2025-11-19 |  | Overdue
TCK-079 | Profile Update | Medium | Assigned | Sneha | 36 | 2025-11-11 07:00 | 2025-11-12 19:00 |  | Overdue
TCK-080 | Course Mapping | Medium | In Progress | Lokesh | 48 | 2025-11-16 17:00 | 2025-11-18 17:00 |  | Overdue
TCK-086 | Course Access Issue | Medium | In Progress | Nisha | 24 | 2025-11-12 03:00 | 2025-11-13 03:00 |  | Overdue

## Dashboard
Status | Count |  |  |  |  | Assigned To | Counnt
New | 23 | Priority | Count | Overdue? | Count | Lokesh | 23
Assigned | 18 | High | 33 | Overdue | 58 | Sneha | 21
In Progress | 17 | Medium | 27 | On-Time | 42 | Arjun | 20
Completed | 27 | Low | 40 |  |  | Rahul | 17
Closed | 15 |  |  |  |  | Nisha | 19